FYP2 TASK CHECKLIST

| GROUP CODE: | SWE/134/24B |
| --- | --- |
| PROJECT TITLE: | StallSeeker |
| GROUP MEMBER: | 1. Adam Danish Bin Muhamad Azizi 2. Adam Fahmi Bin Shari 3. Hairi Hakimi Bin Hasmadi 4. Nur Fadiyah Binti Mohd Fazli |
| SUPERVISOR NAME: | Norulmubarakah Ibrahim |

| No. | TASK | DATE(s) | PERSON IN CHARGE | TICK / ONCE DONE |
| --- | --- | --- | --- | --- |
|  | INFORMATION GATHERING |  |  |  |
| 1 | Confirm the problem statement, project objectives, scope, and success criteria | TBC | Adam Danish, Adam Fahmi, Hairi, Fadiyah |  |
| 2 | Finalise requirements and user stories for customer, vendor, and guest users | TBC | All |  |
| 3 | Complete the system architecture, database design, interface design, and use-case diagrams | TBC | Adam Danish |  |
|  | DEVELOPMENT |  |  |  |
| 4 | Set up the Flutter project structure, dependencies, and application theme | 27/07/2026 | Adam Danish | X |
| 5 | Configure Firebase Core, Authentication, Firestore, and Firebase Storage | 27/07/2026-04/08/2026 | Adam Danish | X |
| 6 | Create the application models, Firestore collection constants, and service layer | 27/07/2026-05/08/2026 | Adam Danish | X |
| 7 | Implement email and password registration and login | 29/07/2026-06/09/2026 | Adam Danish | X |
| 8 | Implement customer and vendor role selection and screen routing | 29/07/2026-06/09/2026 | Adam Danish | X |
| 9 | Implement guest access and Google Sign-In | 06/08/2026-12/08/2026 | Adam Danish | X |
| 10 | Implement email verification, forgotten password, change password, and change email functions | 06/08/2026-06/09/2026 | Adam Danish | X |
| 11 | Develop the vendor profile and stall information management screens | 03/08/2026-14/08/2026 | Adam Danish | X |
| 12 | Implement stall image upload, description, category, and opening-hours management | 03/08/2026-14/08/2026 | Adam Danish | X |
| 13 | Develop the vendor dashboard with location sharing and open or closed stall status | 03/08/2026-25/08/2026 | Adam Danish | X |
| 14 | Develop vendor menu creation, editing, deletion, pricing, images, and availability | 03/08/2026-14/08/2026 | Adam Danish | X |
| 15 | Develop customer stall discovery using GPS and Google Maps | 03/08/2026-06/09/2026 | Adam Danish | X |
| 16 | Implement manual location selection for customers | 12/08/2026-06/09/2026 | Adam Danish | X |
| 17 | Implement stall search, category filters, distance filters, and map-bound filtering | 03/08/2026-06/09/2026 | Adam Danish | X |
| 18 | Develop stall cards and the stall-details screen with menu information | 03/08/2026-06/09/2026 | Adam Danish | X |
| 19 | Implement stall following and unfollowing with a customer following list | 05/08/2026-25/08/2026 | Adam Danish | X |
| 20 | Implement push notifications for vendor stall-status updates | 06/08/2026-06/09/2026 | Adam Danish | X |
| 21 | Implement notification history, unread status, and notification preferences | 06/09/2026 | Adam Danish | X |
| 22 | Add directions through Google Maps, Waze, and browser fallback | 25/08/2026 | Adam Danish | X |
| 23 | Complete profile, account, About, FAQ, legal, logout, and account-deletion screens | 06/08/2026-06/09/2026 | Adam Danish | X |
| 24 | Improve the splash screen, welcome screen, navigation, loading states, and error messages | 06/08/2026-06/09/2026 | Adam Danish | X |
| 25 | Configure production secrets, Firestore rules, indexes, and Cloud Functions deployment | TBC | Adam Danish |  |
| 26 | Prepare the signed Android release build and final installation package | TBC | Adam Danish |  |
|  | TESTING |  |  |  |
| 27 | Run notification-history backend unit tests | 10/09/2026 | Adam Danish | X |
| 28 | Run Flutter static analysis and resolve warnings and errors | TBC | Adam Danish |  |
| 29 | Test registration, verification, login, Google login, guest access, and role routing | TBC | Adam Danish |  |
| 30 | Test vendor profile, stall location, operating status, and menu management | TBC | Adam Danish |  |
| 31 | Test customer location, stall search, filters, details, and directions | TBC | Adam Danish |  |
| 32 | Test following, notifications, notification history, and notification preferences | TBC | Adam Danish |  |
| 33 | Validate Firestore, Storage, and Cloud Functions security permissions | TBC | Adam Danish |  |
| 34 | Conduct Android device, usability, regression, and release-build testing | TBC | Adam Danish |  |
|  | DOCUMENTATION |  |  |  |
| 35 | Update Chapters 1-3 with the final scope, literature review, methodology, and system design | TBC | Adam Danish |  |
| 36 | Write the implementation chapter with architecture and feature evidence | TBC | Adam Danish |  |
| 37 | Write the testing and evaluation chapter with test cases, results, and limitations | TBC | Adam Danish |  |
| 38 | Prepare the user manual and deployment guide | TBC | Adam Danish |  |
| 39 | Update diagrams, screenshots, references, appendices, and traceability evidence | TBC | Adam Danish |  |
| 40 | Proofread and format the final report according to institutional requirements | TBC | Adam Danish |  |
|  | PROGRESS PRESENTATION #1 |  |  |  |
| 41 | Prepare slides, progress evidence, and demonstration flow for Progress Presentation 1 | TBC | Adam Danish |  |
| 42 | Deliver Progress Presentation 1 and record reviewer feedback | TBC | Adam Danish |  |
|  | PROGRESS PRESENTATION #2 |  |  |  |
| 43 | Prepare updated slides, test evidence, and demo for Progress Presentation 2 | TBC | Adam Danish |  |

| No. | TASK | DATE(s) | PERSON IN CHARGE | TICK / ONCE DONE |
| --- | --- | --- | --- | --- |
|  | INTERNAL PRESENTATION |  |  |  |
| 44 | Complete the internal presentation and apply panel corrections | TBC | Adam Danish |  |
|  | EXTERNAL PRESENTATION |  |  |  |
| 45 | Freeze the tested application, report, user manual, slides, and backup demonstration materials | TBC | Adam Danish |  |
| 46 | Deliver the external presentation and final system demonstration | TBC | Adam Danish |  |

(LIST YOUR TASKS AS DETAIL AS POSSIBLE, REFER TO YOUR GANTT CHART)